## MASTER PLAN
Status | ID | Task / Goal | Estimate | Done date
DONE | D01 | 2026-08/09 — 4 brand channels LIVE (Quote Quarry, Investor's Compass, Money Rulebook, Debt-Free Doctrine), 3 Shorts/day each via CI
DONE | D02 | Script brain 5-layer chain (Gemini flash-lite → Groq → Cerebras → Mistral → HuggingFace) |  | 2026-09-07
DONE | D03 | Music engine LIVE (incompetech rotation, per-brand moods, credits auto-appended) |  | 2026-09-08
DONE | D04 | NTFY phone alerts (reports + healing + recycle-needed pushes) |  | 2026-09-08
DONE | D05 | Competitor scan applied (ranking tags + authority titles + psychology theme bank) |  | 2026-09-12
DONE | D06 | Long-video documentary script engine tested (8-12 min, Paulson case study) |  | 2026-09-12
DONE | D07 | Daily Excel report with ALL channels + Video Views sheet (under-1K in red), sent to phone |  | 2026-09-13
DONE | D08 | Sweeper rewritten for the 4 live channels (heals missing reels + token identity guard) |  | 2026-09-13
DONE | D09 | All 4 channel tokens renewed after Sep-12 breakage; secrets re-pushed; all green |  | 2026-09-13
DONE | D10 | Recycler built: quota-skip slot re-uploads the channel's oldest under-1K Short as-is (same file/title/description/tags/thumbnail) |  | 2026-09-13
DONE | D11 | First real recycle cycle completed (Money Rulebook: old 6-view copy hidden → deleted by sweeper) |  | 2026-09-13
DONE | D12 | ARCHIVE PLAN: every new render stored as GitHub Release asset (archive-YYYY-MM) — recycler downloads from GitHub, never YouTube (CI proven) |  | 2026-09-14
DONE | D13 | Archive seeded: 52 old under-1K Shorts stored (all 4 channels) |  | 2026-09-14
DONE | D14 | 7-day minimum age rule for recycles (fresh videos get time to grow) |  | 2026-09-14
DONE | D15 | Safe re-run guard: max 1 recycle per channel per day |  | 2026-09-14
DONE | D16 | Double production FIXED: local 2pm automation disabled; run-all-channels.mjs is a topup helper only (git pull first); CI is the only production master |  | 2026-09-14
DONE | D17 | Legacy 5-brand stack deleted (content-machine, self-heal, run-content-machine, old PDF reporting, wf-*.json) |  | 2026-09-14
DONE | D18 | Deep roadmap research saved (research/roadmap-2026-09-14.md) |  | 2026-09-14
IN PROGRESS |  | TikTok "Quarry Studio" own-app approval (multi-brand publishing product; site + audit kit ready)
IN PROGRESS |  | Archive keeps growing automatically (every new render is stored; no action needed)
TODO |  | T1 — Fix FB photo bug: execFileSync not imported in yt-daily.mjs (FB frame-post feature is silently dead) | 10 min
TODO |  | T2 — ⭐ LONG-FORM documentaries: 1 per week per finance brand (IC/MR/DFD) using the existing long-video engine — finance RPM $4-20 vs Shorts $0.01-0.07 | ~1 day
TODO |  | T3 — Telegram funnel: free bot API, auto-post each Reel + poster per brand; doubles as backup alerts | ~half day
TODO |  | T4 — Community posts: 1 auto post/day per channel (reuse FB posters as quote cards); Communities now open to all channels | ~half day
TODO |  | T5 — Auto-dubbing ON: verify in Studio settings for all 4 channels (free international reach) | 15 min
TODO |  | T6 — "Hype this 🚀" line added to pinned comments (all channels qualify, under 500K subs) | 10 min
TODO |  | T7 — CI caching: Kokoro model + node_modules (saves ~4 min per channel run) | ~half day
TODO |  | T8 — NTFY action buttons (e.g. "Run recycle" button on the phone push) | ~half day
TODO |  | T9 — Excel report: add Recycle/Heal log sheet + weekly per-channel growth sheet | ~half day
TODO |  | T10 — Playlist SEO: auto-create per-theme playlists per channel | ~half day
TODO |  | T11 — Trend-triggered slot: if trend research shows a spike, swap that day's slot-3 theme | ~half day
TODO |  | T12 — Music: lock pool to your approved picks (waiting for your menu selections) + no track twice in one day — 30 min after picks
TODO |  | T13 — Weekly archive top-up: auto-seed 5 oldest under-1K per channel every Sunday | ~half day
TODO |  | T14 — Title A/B on recycles: recycled copy gets a title variant (not identical) | ~half day
TODO |  | T15 — Re-enable daily long-form compilation workflow (currently disabled in GitHub UI — confirm wanted) | 5 min
TODO |  | T16 — Split schedule-state.json into per-channel files (ends merge conflicts) | ~half day
TODO |  | T17 — Monthly competitor scan re-run with auto theme-bank refresh | ~half day
TODO |  | T18 — Quarry Studio dashboard deployed to the cloud (currently localhost only) | ~1 day
BLOCKED |  | B1 — Affiliate links on uploads (needs: your Payoneer KYC + ClickBank/Digistore24 signups)
BLOCKED |  | B2 — Pinterest auto-posting (needs: your Connect-app OAuth, code already wired)
BLOCKED |  | B3 — TikTok posting (needs: Google Play "Quarry Studio" app approval)
BLOCKED |  | B4 — Blog + AdSense (needs: domain purchase ~$10/yr with international card)
BLOCKED |  | B5 — IC channel re-auth for the long-video engine (browser consent step)
IDEA |  | I1 — 15-channel expansion: wire 2-3 dummy channels (1 slot/day each) after a clean production week; put new channels on separate Google accounts (single-email risk)
IDEA |  | I2 — Episode/documentary series per brand (deeper than T2 weekly format)
IDEA |  | I3 — YouTube "Hype" paid promotion experiments when it opens fully in 2026
IDEA |  | I4 — Comment auto-features (auto-heart, template replies) — needs advanced-features unlock
IDEA |  | I5 — Digital product (e-book/course) sold via the finance brands' link slots
IDEA |  | I6 — A/B titles on new uploads (not just recycles) if YouTube Test & Compare exposes an API